# David Lovelace Archive — Project Bid

Progressing the archive: stakeholder liaison, georectification, web development, and outreach

Robin Lovelace

2026-07-03

## Summary

This project will progress the David Lovelace Archive (DLA) from a static prototype to an actively managed, openly accessible resource that serves Herefordshire’s conservation, heritage, and research communities. The project has four workstreams, designed to create lasting value for the county, to improve knowledge of the valuable information in the archive, and ensuring people across the county and beyond can benefit from this unique record.

The David Lovelace Archive is a substantial collection of maps, aerial photography, habitat surveys, veteran tree records, and historical documents assembled over decades by David Lovelace (1948–2026). It represents the most comprehensive non-governmental archive of Herefordshire’s landscape and ecological history. This bid seeks to make it accessible, geospatially enabled, and actively used by the organisations and communities researching and preserving.

Timescale: 12 months.

## Organisations and context

- Herefordshire Meadows — 5 days. Georectification of meadow sites, veteran tree survey data, QGIS training, and open access to archive information.

- Herefordshire Wildlife Trust — 2 days. Habitat survey data, nature reserve boundary overlays, and training in using historic maps for landscape recovery.

- Woolhope Club (Woolhope Naturalists’ Field Club) — part of Robin Lovelace’s project lead time. Archive transfer to their library, access to tithe maps and survey photographs for their 600+ members.

- Herefordshire Archive and Records Centre (HARC) — part of Robin Lovelace’s project lead time. Transfer of priority digital and physical materials, ensuring long-term public access and integration with existing collections.

- Ancient Tree Forum (ATF) — 5 days. LOWVP Veteran Tree Survey made openly accessible and cross-referenced with the Ancient Tree Inventory, ground-truthing field work, and training.

- Homme House, Much Marcle — 2 days (in-kind). Inclusion as a case study site, georectification of estate records, parkland tree data digitisation, and training opportunities.

- Stuart Hedley — Botanical Consultant — 5 days. Access to the archive’s botanical and habitat records for VC36 recording, training in QGIS for field botany, and integration with Herefordshire Meadows work.

- CPRE Herefordshire — 5 days. Historic landscape archive data, georectification of CPRE-relevant maps and CPRE landscape photographs, and training in using historic maps for landscape advocacy.

## Workstreams

### Workstream 1: Stakeholder liaison and archive prioritisation

Workstream 1 — Stakeholder liaison and prioritisation effort

| Person | Days | Role |
| --- | --- | --- |
| Robin Lovelace | 4 | Project lead; stakeholder meetings with HARC, Woolhope Club, others |
| Stuart Hedley | 5 | Botanical audit; identify priority meadows and woodland surveys |
| Ancient Tree Forum | 2 | Audit veteran tree survey data; identify priority parishes for release |
| Herefordshire Meadows | 2 | Identify meadow restoration sites with matching archival records |
| Herefordshire Wildlife Trust | 1 | Identify nature reserve overlap with archive habitat data |
| Homme House | 1 | Identify veteran parkland trees and estate records for inclusion |
| CPRE Herefordshire | 2 | Identify priority historic landscapes and CPRE photo archive content |

Activities:

- Stakeholder meetings to agree priorities and data needs.

- Archive audit per stakeholder conservation and research remit.

- Prioritisation matrix, publication schedule, and materials transfer to HARC and Woolhope Club.

### Workstream 2: Georectification of historic maps and aerial photography

Workstream 2 — Georectification effort

| Person | Days | Role |
| --- | --- | --- |
| Robin Lovelace | 4 | Lead georectification; QGIS processing; PMTiles pipeline |
| Ancient Tree Forum | 2 | Ground-truth veteran tree locations; verify historic grid references |
| Herefordshire Meadows | 2 | Provide meadow boundary data for historic map overlay |
| Herefordshire Wildlife Trust | 1 | Provide nature reserve boundary data |
| Homme House | 1 | Provide parkland boundary and veteran tree location data |
| CPRE Herefordshire | 2 | Provide CPRE landscape photo locations and historic landscape data |

Activities:

- Georectify priority tithe maps (Kings Caple, Clifford, selected parishes).

- Georectify RAF 1947 and Luftwaffe aerial photography covering priority areas.

- Create PMTiles and COGs for web deployment.

- Ground-truth selected historic features with stakeholder partners.

- Publish as browsable, interactive map layers on the archive website.

- Cross-reference veteran tree survey with the Ancient Tree Inventory for ATF’s national network.

### Workstream 3: Outreach, QGIS training, and research initiation

Workstream 3 — Outreach and research effort

| Person | Days | Role |
| --- | --- | --- |
| Robin Lovelace | 3 | Design and deliver QGIS training; academic liaison; workshop coordination |
| Ancient Tree Forum | 1 | Contribute veteran tree survey methods to workshop content |
| Herefordshire Meadows | 1 | Co-host meadow-focused session; engage network of land managers |
| CPRE Herefordshire | 1 | Contribute historic landscape perspective and CPRE use cases |

Activities:

- David Lovelace Archive Workshop — 1–2 day QGIS beginner workshop: loading georectified maps, overlaying modern boundaries, digitising historic features, and mobile field data capture.

- Stakeholders (Herefordshire Meadows, ATF, CPRE, Woolhope Club, Homme House) contribute use cases from their own sites and datasets.

- Academic liaison with University of Leeds ITS and other partners to identify at least one research project from the archive — measuring change in veteran tree populations, field boundary loss, or woodland continuity over 150+ years.

- Workshop materials (data packs, QGIS project files, video guides) published openly for reuse.

### Workstream 4: Web development — asset geolocation and hosting

Workstream 4 — Web development effort

| Person | Days | Role |
| --- | --- | --- |
| Robin Lovelace | 4 | Lead developer; geolocation feature implementation; deployment |

Activities:

- Asset geolocation — browsable, searchable map interface with spatial filtering by parish, grid square, and stakeholder area of interest.

- Hosting pipeline for PMTiles and COG layers from WS2, published at no ongoing cost via Netlify, GitHub Pages, or similar.

- Download portal for bulk data access — researchers and partners can retrieve archive content without manual file requests.

- Long-term sustainability — clean archive (~2.4 TB on Leeds server) served via GitHub Releases and static hosting.

## Resource summary

Resource allocation by person and workstream (days)

| Person | WS1 | WS2 | WS3 | WS4 | Total |
| --- | --- | --- | --- | --- | --- |
| Robin Lovelace | 4 | 4 | 3 | 4 | 15 |
| Stuart Hedley | 5 | 0 | 0 | 0 | 5 |
| Ancient Tree Forum | 2 | 2 | 1 | 0 | 5 |
| Herefordshire Meadows | 2 | 2 | 1 | 0 | 5 |
| Homme House | 1 | 1 | 0 | 0 | 2 |
| Herefordshire Wildlife Trust | 1 | 1 | 0 | 0 | 2 |
| CPRE Herefordshire | 2 | 2 | 1 | 0 | 5 |

Total person-days: 39

## Timeline (12 months)

| Quarter | Workstream focus | Key milestones |
| --- | --- | --- |
| Q1 (Months 1–3) | WS1: Stakeholder liaison | Initial meetings, archive audit, prioritisation, transfer agreements signed |
| Q2 (Months 4–6) | WS2: Georectification | Priority tithe maps and aerial photos georectified; first PMTiles published |
| Q3 (Months 7–9) | WS3: Outreach + WS4: Web dev | QGIS workshop delivered; asset geolocation feature live; data transferred to HARC |
| Q4 (Months 10–12) | All | Cross-referencing complete; materials transferred to Woolhope Club and partners; project report |

## Proposed budget

| Item | Days | Day rate (£) | Total (£) |
| --- | --- | --- | --- |
| Robin Lovelace | 15 | TBC | TBC |
| Stuart Hedley | 5 | TBC | TBC |
| Ancient Tree Forum | 5 | TBC | TBC |
| Herefordshire Meadows | 5 | TBC | TBC |
| Herefordshire Wildlife Trust | 2 | TBC | TBC |
| Homme House | 2 days in-kind | — | — |
| CPRE Herefordshire | 5 | TBC | TBC |
| Total | 39 |  | TBC |

## Next steps

- Confirm stakeholder interest, availability, and in-kind commitments.

- Finalise day rates and budget figures.

- Submit to Brightspace Foundation (first instance).

- On award: recruit project team, schedule initial stakeholder roundtable, and begin archive audit.